## Project Status Dashboard
PROJECT NAME |  |  |  | DATE | PROJECT STATUS | % COMPLETE
Final Resource Plan |  |  |  | 2025-04-05 | Not Found | #N/A
TASK TIMELINE
DASHBOARD DATA
TASK TABLE
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS | STATUS | PRIORITY
Set kick-off meeting |  | 2025-03-22 | 2025-04-01 | 10 | Complete | High |  | Not Started | High
Agree on objectives |  | 2025-03-28 | 2025-04-05 | 8 | Complete | Medium |  | In Progress | Medium
Detailed Reqs. |  | 2025-03-25 | 2025-04-07 | 13 | Complete | Low |  | Complete | Low
Hardware Reqs. |  | 2025-03-31 | 2025-04-09 | 9 | Complete | Low |  | Overdue
Final Resource Plan |  | 2025-04-01 | 2025-04-10 | 9 | Complete | Low |  | On Hold
Staffing |  | 2025-04-04 | 2025-04-16 | 12 | Overdue | High
Technical Reqs. |  | 2025-04-05 | 2025-04-12 | 7 | In Progress | High
Testing |  | 2025-04-07 | 2025-04-18 | 11 | In Progress | High
Dev. Complete |  | 2025-04-08 | 2025-04-25 | 17 | In Progress | High
Hardware Config. |  | 2025-04-19 | 2025-04-26 | 7 | On Hold | High
System Testing |  | 2025-04-24 | 2025-04-25 | 1 | Not Started | High
Launch |  | 2025-04-26 | 2025-04-27 | 1 | Not Started | Medium
TASK STATUS % |  |  |  | BUDGET
STATUS | COUNT | % |  | PLANNED | 80000
Not Started | 2 | 16.67% |  | ACTUAL | 50000
In Progress | 3 | 25%
Complete | 5 | 41.67%
Overdue | 1 | 8.333%
On Hold | 1 | 8.333%
TOTAL | 12 | 100%
TASK PRIORITY % |  |  |  | PENDING ITEMS
PRIORITY | COUNT | % |  | Decisions | 5
High | 7 | 58.33% |  | Actions | 2
Medium | 2 | 16.67% |  | Change Requests | 4
Low | 3 | 25%
| 0 | 0%
TOTAL | 12 | 100%